## Introduction
Deloitte Digital
Project Review - Reporting template
Project Detail
Service Line
| Project Name | <Project_Name>
LEP
Onsite Project Manager
Review Detail
Reviewer Name
| Current Review Date (MM/DD/YYYY) |  | Effort Spent on Review (hrs)
Next Review Start Date (MM/DD/YYYY)

## Guideline
Deloitte Digital
|  |  |  | Indicator | Importancy | Metric status | Guideline
| Empire time | G | Empire timeG | Empire time | Low | Green | 100% of the team register their timesheet in Empire time
| Empire time | A | Empire timeA |  |  | Amber | The timesheet is registered in Empire time between 80% - 100% of the team
| Empire time | R | Empire timeR |  |  | Red | Less the 80% from the team registered the timesheet in Empire Time
| Delivery | G | DeliveryG | Delivery | High | Green | More then 90% of the user stories from the current sprint were delivered
| Delivery | A | DeliveryA |  |  | Amber | We have delivered between 75% and 90% from the total user stories of the current sprint
| Delivery | R | DeliveryR |  |  | Red | Less than 75% of the user stories from the current sprint was delivered
| Attrition | G | AttritionG | Attrition | Medium | Green | Regrettable attrition is lower than 10%
| Attrition | A | AttritionA |  |  | Amber | Regrettable attrition is between 10% - 20%
| Attrition | R | AttritionR |  |  | Red | Regrettable attrition si bigger than 20%
| Invoicing | G | InvoicingG | Invoicing | Low | Green | There are no invoices outstanding before 30 days
| Invoicing | A | InvoicingA |  |  | Amber | There are invoices outstanding between 30-60 days
| Invoicing | R | InvoicingR |  |  | Red | There are invoices outstanding for more than 60 days
| Stakeholders | G | StakeholdersG | Stakeholders | High | Green | There is no escalation from the stakeholderss
| Stakeholders | A | StakeholdersA |  |  | Amber | Escalation at maximum Senior Manager level
| Stakeholders | R | StakeholdersR |  |  | Red | Escalation at Director/Partner level
| Change order | G | Change orderG | Change order | Medium | Green | Change order signed that covers the current day for the entire team
| Change order | A | Change orderA |  |  | Amber | Change order will expire in the following 30 days
| Change order | R | Change orderR |  |  | Red | Change order is expired
| Test Code Coverage | G | Test Code CoverageG | Test Code Coverage | Medium | Green | Test code coverage is at least 80%
| Test Code Coverage | A | Test Code CoverageA |  |  | Amber | Test code coverage is between 51% and 79%
| Test Code Coverage | R | Test Code CoverageR |  |  | Red | Test code coverage is lower than 50%
| Branch coverage | G | Branch coverageG | Branch coverage | Medium | Green | Statement/Branch Coverage is at least 80%
| Branch coverage | A | Branch coverageA |  |  | Amber | Statement/Branch Coverage is between 51% and 79%
| Branch coverage | R | Branch coverageR |  |  | Red | Statement/Branch Coverage is lower than 50%
| Density of Duplication | G | Density of DuplicationG | Density of Duplication | Medium | Green | Duplication percentage is lower than 50%
| Density of Duplication | A | Density of DuplicationA |  |  | Amber | Duplication percentage is between 51% and 79%
| Density of Duplication | R | Density of DuplicationR |  |  | Red | Duplication percentage is higher than 80%
|  |  |  | RISK OVERALL STATUS |  | Green | Low
[6 empty] | Amber | Medium
[6 empty] | Red | High

## Metrics
Deloitte Digital
1 |  | Empire time
|  | Empire time | Value % |  | Status
| Empire time |  | 100 |  |  |  | G
2 |  | Delivery
|  | Delivery | Value % |  | Status
| Delivery |  | 90 |  |  |  | A
3 |  | Attrition
|  | Attrition | Value % |  | Status
| Attrition |  | 15 |  |  |  | A
[8 empty] | RISK OVERALL STATUS |  | A
4 |  | Invoices
|  |  | Please select |  | Status |  |  |  | MEDIUM RISK
|  | Invoicing | No invoices outstanding before 30 days
| Invoicing | [5 empty] | G
5 |  | Stakeholders
|  |  | Please select seniority | Please select Root cause | Status
|  | Escalation | Senior manager level | People
| Escalation |  |  |  |  | 6 | A
6 |  | Change order
|  |  | Please select |  | Status
|  | Change order | Covers the current day
| Change order | [5 empty] | G
7 |  | Test code Coverage
|  | Test code Coverage | Value % |  | Status
| Test code Coverage |  | 70 |  |  |  | A
8 |  | Statement/Branch Coverage
|  | Branch Coverage | Value % |  | Status
| Branch Coverage |  | 100 |  |  |  | G
9 |  | Density of Duplication
|  | Density of Duplication | Value% |  | Status
| Density of Duplication |  | 50 |  |  |  | G

## Risks
Deloitte Digital
| Risk description | Risk Type | Impact | Probability | Score - product | Risk | Risk | Action | Owner | Due Date
| The project has no roadmap | Delivery | 5 | 5 | 25 | R |  | Talk with the Product Owner | Ioan P | 10.03.2019
|  | People | 5 | 3 | 15 | A
|  |  | 3 | 4 | 12 | G

## Power point
Deloitte Digital
| Empire TimeG | Empire Time | 100% of the team register their timesheet in Empire time | Empire time | G
| DeliveryA | Delivery | We have delivered between 75% and 90% from the total user stories of the current sprint | Delivery | A | Contract Type
| AttritionA | Attrition | Regrettable attrition is between 10% - 20% | Attrition | A | ERDC Project Status (Overall) |  |  | A
| InvoicingG | Invoicing | There are no invoices outstanding before 30 days | Invoicing | G | WO/CO expiry date & status | 31.12.2018 | STATUS
| StakeholdersA | Stakeholders | Escalation at maximum Senior Manager level | Escalation | A | Scheduled End Date | 10.08.2019
| Change orderG | Change order | Change order signed that covers the current day for the entire team | Change order | G
| Test code CoverageA | Test code Coverage | Test code coverage is between 51% and 79% | Test code Coverage | A
| Branch CoverageG | Branch Coverage | Statement/Branch Coverage is at least 80% | Branch Coverage | G
| Density of DuplicationG | Density of Duplication | Duplication percentage is lower than 50% | Density of Duplication | G

## SonarQube Metrics
Deloitte Digital
| Project Name | Sprint Name / No | Resource Count | Sprint Duration | Sprint Completion Date | Test Code Coverage | Line Coverage / Statement Coverage | Condition Coverage | Duplication (%) / Density of duplication
| Project 1 | 1 | 12 | 2Weeks | 2016-04-15 | 87% | 87% | 87% | 87%
| Project 1 | 2 | 12 | 2Weeks | 2016-04-29 | 82% | 82% | 82% | 82%
| Project 1 | 3 | 12 | 2Weeks | 2016-05-13 | 89% | 89% | 89% | 89%
| Project 1 | 4 | 12 | 3Weeks | 2016-06-03 | 94% | 94% | 94% | 94%
| Project 1 | 5 | 12 | 3Weeks | 2016-06-24 | 96% | 96% | 96% | 96%
| Project 1 | 6 | 12 | 3Weeks | 2016-07-15 | 99% | 99% | 99% | 99%
| Project 1 | 7 | 12 | 3Weeks | 2016-08-05 | 100% | 100% | 100% | 100%
| Project 1 | 8 | 15 | 2Weeks | 2016-08-19 | 76% | 76% | 76% | 76%
| Project 1 | 9 | 15 | 2Weeks | 2016-09-02 | 89% | 89% | 89% | 89%
| Project 1 | 10 | 15 | 2Weeks | 2016-09-16 | 97% | 97% | 97% | 97%
| Project 1 | 11 | 15 | 2Weeks | 2016-09-30 | 100% | 100% | 100% | 100%
| Project 1 | 12 | 15 | 2Weeks | 2016-10-14 | 100% | 100% | 100% | 100%
| Project 1 | 13 | 15 | 3Weeks | 2016-11-04 | 100% | 100% | 100% | 100%
| Project 1 | 14 | 15 | 3Weeks | 2016-11-25 | 88% | 88% | 88% | 88%
| Project 1 | 15 | 15 | 3Weeks | 2016-12-16 | 86% | 86% | 86% | 86%
| Project 1 | 16 | 13 | 3Weeks | 2017-01-06 | 85% | 85% | 85% | 85%
| Project 1 | 17 | 13 | 3Weeks | 2017-01-27 | 99% | 99% | 99% | 99%
| Project 1 | 18 | 13 | 3Weeks | 2017-02-17 | 97% | 97% | 97% | 97%
| Project 1 | 19 | 13 | 3Weeks | 2017-03-10 | 88% | 88% | 88% | 88%
| Project 1 | 20 | 13 | 3Weeks | 2017-03-31 | 87% | 87% | 87% | 87%
| Project 1 | 21 | 13 | 3Weeks | 2017-04-21 | 90% | 90% | 90% | 90%
| Project 1 | 22 | 13 | 3Weeks | 2017-05-12 | 96% | 96% | 96% | 96%
| Project 1 | 23 | 13 | 1 Week | 2017-05-19 | 97% | 97% | 97% | 97%
| Project 1 | 24 | 11 | 1 Week | 2017-05-26 | 100% | 100% | 100% | 100%
| Project 1 | 25 | 11 | 1 Week | 2017-06-02 | 100% | 100% | 100% | 100%
| Project 1 | 26 | 23 | 2Weeks | 2017-06-03 | 70% | 10% | 100% | 100%
Note on D4: Count of resources whose capacity is considered for this sprint
Note on E4: Total no of days for current sprint

## SonarQube Dashboard
Total Test Code Coverage %
Statement Coverage %
Decision Coverage %
Density of Duplication

## workingSheet (hidden)
No invoices outstanding before 30 days |  | Green | G
Invoices outstanding between 31-60 days |  | Amber | A
Invoices outstanding for more than 60 days |  | Red | R
No escalation | 0
Manager level | 1 | 1
Senior manager level | 3 | 2
Director | 4 | 3
Partner | 5 | 4
5
Delivery | 2
People | 2
Invoicing | 1
Covers the current day
Expire in the following 30 days
Is expired
Important
Less important
Very Important
Empire Time | Empire time
Delivery | Delivery
Attrition | Attrition
Invoicing | Invoicing
Stakeholders | Escalation
Change order | Change order
Test code Coverage | Test code Coverage
Branch Coverage | Branch Coverage
Density of Duplication | Density of Duplication
Delivery
People